## Summary
Phase | Duration (weeks) | Total Hours | Person-Weeks | Start Date | End Date | Team
Phase 1: Planning & Design | 2 | 290 | 7.2 | 2025-11-10 | 2025-11-24 | Backend Dev (1), Designer (1), PM (1)
Phase 2: Backend Development | 8 | 780 | 19.5 | 2025-11-24 | 2026-01-19 | Backend Dev (2), DevOps (0.5)
Phase 3: Mobile App Development | 10 | 860 | 21.5 | 2025-11-24 | 2026-02-02 | Mobile Dev (2), Designer (0.5)
Phase 4: Web Development | 8 | 730 | 18.2 | 2025-12-08 | 2026-02-02 | Frontend Dev (2), Designer (0.5)
Phase 5: Integration & Testing | 4 | 540 | 13.5 | 2025-12-08 | 2026-01-05 | QA (2), All Devs (3), DevOps (1)
Phase 6: Deployment | 2 | 270 | 6.8 | 2026-02-02 | 2026-02-16 | DevOps (1), QA (2), PM (1), All Devs (1)
Phase 7: Post-Launch Support | 4 | 260 | 6.5 | 2026-03-02 | 2026-03-30 | All Devs (2), DevOps (0.5), QA (1)

## Detailed Tasks
Phase | Task | Hours | Days | Resource | Start Date | End Date
Phase 1: Planning & Design | Requirements Documentation | 40 | 5 | PM + Team | 2025-11-10 | 2025-11-24
Phase 1: Planning & Design | Database Schema Design | 60 | 7.5 | 1 Backend Dev | 2025-11-10 | 2025-11-24
Phase 1: Planning & Design | API Specifications | 50 | 6.2 | 1 Backend Dev | 2025-11-10 | 2025-11-24
Phase 1: Planning & Design | UI/UX Refinement | 80 | 10 | 1 Designer | 2025-11-10 | 2025-11-24
Phase 1: Planning & Design | Architecture Documentation | 40 | 5 | 1 Backend Dev | 2025-11-10 | 2025-11-24
Phase 1: Planning & Design | Sprint Planning | 20 | 2.5 | PM | 2025-11-10 | 2025-11-24
Phase 2: Backend Development | Database Setup & Migrations | 60 | 7.5 | 1 Backend Dev | 2025-11-24 | 2026-01-19
Phase 2: Backend Development | Authentication System | 80 | 10 | 1 Backend Dev | 2025-11-24 | 2026-01-19
Phase 2: Backend Development | User Management APIs | 60 | 7.5 | 1 Backend Dev | 2025-11-24 | 2026-01-19
Phase 2: Backend Development | Product Catalog APIs | 80 | 10 | 1 Backend Dev | 2025-11-24 | 2026-01-19
Phase 2: Backend Development | Order Management System | 120 | 15 | 2 Backend Devs | 2025-11-24 | 2026-01-19
Phase 2: Backend Development | Payment Gateway Integration | 100 | 12.5 | 1 Backend Dev | 2025-11-24 | 2026-01-19
Phase 2: Backend Development | Delivery Management | 80 | 10 | 1 Backend Dev | 2025-11-24 | 2026-01-19
Phase 2: Backend Development | Admin Panel APIs | 100 | 12.5 | 1 Backend Dev | 2025-11-24 | 2026-01-19
Phase 2: Backend Development | Loyalty Points Engine | 60 | 7.5 | 1 Backend Dev | 2025-11-24 | 2026-01-19
Phase 2: Backend Development | Notification Service | 40 | 5 | 1 Backend Dev | 2025-11-24 | 2026-01-19
Phase 3: Mobile App Development | Flutter Project Setup | 40 | 5 | 1 Mobile Dev | 2025-11-24 | 2026-02-02
Phase 3: Mobile App Development | Authentication Screens | 60 | 7.5 | 1 Mobile Dev | 2025-11-24 | 2026-02-02
Phase 3: Mobile App Development | Home Feed & Navigation | 80 | 10 | 1 Mobile Dev | 2025-11-24 | 2026-02-02
Phase 3: Mobile App Development | Product Browse & Search | 100 | 12.5 | 1 Mobile Dev | 2025-11-24 | 2026-02-02
Phase 3: Mobile App Development | Custom Box Builder | 120 | 15 | 2 Mobile Devs | 2025-11-24 | 2026-02-02
Phase 3: Mobile App Development | Shopping Cart & Checkout | 80 | 10 | 1 Mobile Dev | 2025-11-24 | 2026-02-02
Phase 3: Mobile App Development | Payment Integration | 80 | 10 | 1 Mobile Dev | 2025-11-24 | 2026-02-02
Phase 3: Mobile App Development | Order Tracking UI | 60 | 7.5 | 1 Mobile Dev | 2025-11-24 | 2026-02-02
Phase 3: Mobile App Development | Profile & Wallet | 60 | 7.5 | 1 Mobile Dev | 2025-11-24 | 2026-02-02
Phase 3: Mobile App Development | Loyalty Rewards UI | 60 | 7.5 | 1 Mobile Dev | 2025-11-24 | 2026-02-02
Phase 3: Mobile App Development | Push Notifications | 40 | 5 | 1 Mobile Dev | 2025-11-24 | 2026-02-02
Phase 3: Mobile App Development | Recipe Sharing Features | 80 | 10 | 1 Mobile Dev | 2025-11-24 | 2026-02-02
Phase 4: Web Development | Next.js Setup with SSR | 40 | 5 | 1 Frontend Dev | 2025-12-08 | 2026-02-02
Phase 4: Web Development | Authentication Pages | 50 | 6.2 | 1 Frontend Dev | 2025-12-08 | 2026-02-02
Phase 4: Web Development | Home & Navigation | 60 | 7.5 | 1 Frontend Dev | 2025-12-08 | 2026-02-02
Phase 4: Web Development | Product Catalog | 80 | 10 | 1 Frontend Dev | 2025-12-08 | 2026-02-02
Phase 4: Web Development | Custom Box Creator | 100 | 12.5 | 1 Frontend Dev | 2025-12-08 | 2026-02-02
Phase 4: Web Development | Checkout Flow | 80 | 10 | 1 Frontend Dev | 2025-12-08 | 2026-02-02
Phase 4: Web Development | User Dashboard | 60 | 7.5 | 1 Frontend Dev | 2025-12-08 | 2026-02-02
Phase 4: Web Development | Order Management | 60 | 7.5 | 1 Frontend Dev | 2025-12-08 | 2026-02-02
Phase 4: Web Development | Admin Dashboard | 120 | 15 | 2 Frontend Devs | 2025-12-08 | 2026-02-02
Phase 4: Web Development | Analytics & Reporting | 80 | 10 | 1 Frontend Dev | 2025-12-08 | 2026-02-02
Phase 5: Integration & Testing | API Integration Testing | 80 | 10 | 1 QA | 2025-12-08 | 2026-01-05
Phase 5: Integration & Testing | Cross-platform Testing | 100 | 12.5 | 2 QA | 2025-12-08 | 2026-01-05
Phase 5: Integration & Testing | Payment Gateway Testing | 60 | 7.5 | 1 QA + 1 Dev | 2025-12-08 | 2026-01-05
Phase 5: Integration & Testing | E2E User Testing | 80 | 10 | 2 QA | 2025-12-08 | 2026-01-05
Phase 5: Integration & Testing | Performance Optimization | 60 | 7.5 | 1 Backend + 1 Frontend | 2025-12-08 | 2026-01-05
Phase 5: Integration & Testing | Security Audit | 40 | 5 | 1 DevOps | 2025-12-08 | 2026-01-05
Phase 5: Integration & Testing | Bug Fixes | 120 | 15 | All Devs | 2025-12-08 | 2026-01-05
Phase 6: Deployment | Server Setup | 40 | 5 | 1 DevOps | 2026-02-02 | 2026-02-16
Phase 6: Deployment | Database Migration | 30 | 3.8 | 1 Backend Dev + DevOps | 2026-02-02 | 2026-02-16
Phase 6: Deployment | App Store Submissions | 40 | 5 | 1 Mobile Dev | 2026-02-02 | 2026-02-16
Phase 6: Deployment | Web Hosting & CDN | 30 | 3.8 | 1 DevOps | 2026-02-02 | 2026-02-16
Phase 6: Deployment | Beta Testing | 60 | 7.5 | 2 QA | 2026-02-02 | 2026-02-16
Phase 6: Deployment | Launch Preparation | 30 | 3.8 | PM + Team | 2026-02-02 | 2026-02-16
Phase 6: Deployment | Documentation | 40 | 5 | All Devs | 2026-02-02 | 2026-02-16
Phase 7: Post-Launch Support | Bug Monitoring | 80 | 10 | 1 Backend + 1 Mobile | 2026-03-02 | 2026-03-30
Phase 7: Post-Launch Support | User Feedback Implementation | 60 | 7.5 | All Devs | 2026-03-02 | 2026-03-30
Phase 7: Post-Launch Support | Performance Monitoring | 40 | 5 | 1 DevOps | 2026-03-02 | 2026-03-30
Phase 7: Post-Launch Support | Minor Enhancements | 80 | 10 | All Devs | 2026-03-02 | 2026-03-30